## Sheet1
User Story/Tasks | Description | Estimated Effort | Sprint | Calendar Days | JIRA Cards Assigned | JIRA Cards Completed | JIRA Cards Not Completed (End of Sprint) | Planned Story Points | Actual
SEN-6 | Sign Up | 3 | Sprint 2 | 2020-10-03 | SEN-21, SEN-22, SEN-23 |  |  | 85 | 85
SEN-7 | Log In | 3 |  | 2020-10-04 |  |  |  | 82.9268 | 85
SEN-8 | View Profile | 2 |  | 2020-10-05 |  |  |  | 80.8537 | 85
SEN-9 | Nav Bar | 1 |  | 2020-10-06 |  | SEN-21, SEN-22 |  | 78.7805 | 80
SEN-10 | Auth Nav Bar | 2 |  | 2020-10-07 |  |  |  | 76.7073 | 80
SEN-11 | Search Ingredient | 3 |  | 2020-10-08 |  | SEN-23 |  | 74.6341 | 77
SEN-12 | Ingredients category | 4 |  | 2020-10-09 |  |  |  | 72.561 | 77
SEN-13 | Save list of ingredients | 2 | Sprint 3 | 2020-10-10 |  |  |  | 70.4878 | 77
SEN-14 | Open saved lists (auth) | 2 |  | 2020-10-11 |  |  |  | 68.4146 | 77
SEN-15 | Add/Remove Ingredients | 3 |  | 2020-10-12 |  |  |  | 66.3415 | 77
SEN-16 | Clear All ingredients | 1 |  | 2020-10-13 |  |  |  | 64.2683 | 77
SEN-17 | How it works page | 2 |  | 2020-10-14 |  |  |  | 62.1951 | 77
SEN-18 | Recipe search | 3 |  | 2020-10-15 |  |  |  | 60.122 | 77
SEN-19 | Save recipes (Auth) | 3 |  | 2020-10-16 |  |  |  | 58.0488 | 77
SEN-20 | Search/filter recipes | 4 | Sprint 4 | 2020-10-17 |  |  |  | 55.9756 | 77
SEN-21 | Endpoints to get recipes | 3 |  | 2020-10-18 |  |  |  | 53.9024 | 77
SEN-22 | Set up Git + Frontend | 2 |  | 2020-10-19 |  |  |  | 51.8293 | 77
SEN-23 | Set up Flask + Backend | 3 |  | 2020-10-20 |  |  |  | 49.7561 | 77
SEN-24 | Home Page Banner | 3 |  | 2020-10-21 |  |  |  | 47.6829 | 77
SEN-25 | - | 0 |  | 2020-10-22 |  |  |  | 45.6098 | 77
SEN-26 | Navigation on banner | 2 |  | 2020-10-23 |  |  |  | 43.5366 | 77
SEN-27 | How to Page | 1 | Sprint 5 | 2020-10-24 | SEN-10, SEN-24, SEN-26, SEN-6, SEN-7, SEN-9, SEN-15, SEN-12, SEN-11, SEN-16, SEN-27, SEN-18, SEN-15 |  |  | 41.4634 | 77
SEN-28 | Recipe component | 6 |  | 2020-10-25 | SEN-28 | SEN-24, SEN-26, SEN-9 |  | 39.3902 | 71
SEN-29 | Buttons for ingredients | 1 |  | 2020-10-26 |  | SEN-28 |  | 37.3171 | 65
SEN-30 | Search bar (ingredients) | 2 |  | 2020-10-27 |  |  |  | 35.2439 | 65
SEN-31 | Categories for ingredients | 2 |  | 2020-10-28 |  | SEN-15, SEN-12, SEN-11, SEN-16 |  | 33.1707 | 54
SEN-32 | Selected ingred to top | 2 |  | 2020-10-29 |  |  |  | 31.0976 | 54
SEN-33 | Search all ingredients | 2 |  | 2020-10-30 |  |  | SEN-10, SEN-6, SEN-7, SEN-27, SEN-18 | 29.0244 | 54
SEN-34 | Create all category | 3 | Sprint 6 | 2020-10-31 | SEN-10, SEN-6, SEN-7, SEN-27, SEN-18, SEN-14, SEN-17, SEN-19, SEN-20, SEN-29, SEN-30, SEN-31, SEN-32, SEN-33, SEN-34, SEN-35, SEN-36 |  |  | 26.9512 | 54
SEN-35 | Payload to backend | 1 |  | 2020-11-01 |  | SEN-29, SEN-30, SEN-31 |  | 24.878 | 49
SEN-36 | Connect front/backend | 5 |  | 2020-11-02 |  | SEN-33 |  | 22.8049 | 47
SEN-37 | Fix responsiveness | 2 |  | 2020-11-03 |  | SEN-32, SEN-34, SEN-35 |  | 20.7317 | 41
SEN-38 | More photos to save recip | 1 |  | 2020-11-04 |  |  |  | 18.6585 | 41
SEN-39 | How it works -> Saved Rec | 1 |  | 2020-11-05 |  |  |  | 16.5854 | 41
SEN-40 | Fix signup / login | 2 |  | 2020-11-06 |  |  | SEN-6, SEN-7, SEN-10, SEN-27, SEN-18, SEN-14, SEN-17, SEN-19, SEN-20, SEN-36 | 14.5122 | 41
SEN-41 | Ingredients to top | 1 | Sprint 7 | 2020-11-07 | SEN-6, SEN-7, SEN-8, SEN-10, SEN-27, SEN-18, SEN-14, SEN-17, SEN-19, SEN-20, SEN-36, SEN-37, SEN-38, SEN-39, SEN-40, SEN-41, SEN-42 | SEN-41 |  | 12.439 | 40
SEN-42 | Fix calling API | 2 |  | 2020-11-08 |  |  |  | 10.3659 | 40
|  |  |  | 2020-11-09 |  | SEN-36, SEN-37, SEN-38 |  | 8.2927 | 32
|  |  |  | 2020-11-10 |  | SEN-42 |  | 6.2195 | 30
|  |  |  | 2020-11-11 |  | SEN-6, SEN-7, SEN-8 |  | 4.1463 | 22
|  |  |  | 2020-11-12 |  | SEN-10, SEN-39, SEN-40 |  | 2.0732 | 17
|  |  |  | 2020-11-13 |  | SEN-13, SEN-14, SEN-18, SEN-19, SEN-20 | SEN-17, SEN-27 | 0 | 3